## GanttChart_pesquisa
|  | Project | Name - Release 1
|  | Project Start Date | 2025-06-30 |  |  |  |  | Display Week | 1
|  | Project End Date | 2025-11-28 | [6 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13
|  | Project Lead | João | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
SENAI IoT | TASK | ISSUE JIRA | LEAD | PREDECESSOR | ISSUE - MIG/UNIF | START WEEK | WEEKS | END WEEK | % DONE | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22
1 | Revisão do problema |  |  |  |  | 1 | 4 | 4 | 0%
1.1 | Garantir a integridade de cargas sensíveis durante o transporte. |  | Emanuelly,Gustavo e Renan |  |  | 1 | 2 | 2 | 0%
1.2 | Redução de perdas financeiras, aumento da confiabilidade no transporte, melhoria da satisfação do cliente |  | Emanuelly,Gustavo e Renan |  |  | 1 | 2 | 2 | 0%
1.3 | Microcontroladores (ESP32), sensores de vibração (MPU-6050, acelerômetros piezoelétricos), sistema de alerta, plataforma de visualização. |  | Emanuelly,Gustavo e Renan |  | WTPD-3589 | 2 | 1 | 2 | 0%
1.4 | Teste em rota com cargas de referência para medir níveis de vibração aceitáveis. |  | Emanuelly,Gustavo e Renan |  |  | 2 | 1 | 2 | 0%
2 | Desenvolvimentos |  |  |  |  | 4 | 2 | 5 | 0%
2.1 | Seleção e fixação dos acelerômetros nos pontos críticos do caminhão/pallet. |  |  |  |  | 4 | 2 | 5 | 0%
2.2 | Aquisição de dados de vibração, filtragem e envio via MQTT. |  |  |  |  | 4 | 2 | 5 | 0%
2.3 | Comunicação via Wi-Fi/4G, protocolos MQTT com TLS. |  |  |  |  | 4 | 2 | 5 | 0%
2.4 | Dashboard com gráficos em tempo real, históricos e relatórios
3 | Testes e Documentação |  |  |  |  | 6 | 1 | 6 | 0%
3.1 | Verificação em bancada e em rota real. |  |  |  |  | 6 | 1 | 6 | 0%
3.2 | Após funcionamento, realizar documentação (GitHub, relatórios) |  |  |  |  | 6 | 1 | 6 | 0%
3.3 | Documentação de desenvolvimentos – registrando versões no GitHub |  |  | 3.2 |  | 6 | 1 | 6 | 0%
3.4 | Explicação para a equipe de logística de como interpretar os dados e agir diante dos alertas.
Note on A7: ====== ID#AAABnjvk7MY Vertex42 (2025-07-22 00:09:24) Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: ====== ID#AAABnjvk7Mg Vertex42 (2025-07-22 00:09:24) Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: ====== ID#AAABnjuPPF4 Vertex42 (2025-07-22 00:09:24) Task Lead Enter the name of the Task Lead in this column.
Note on E7: ====== ID#AAABnjuPPGI Predecessor Tasks (2025-07-22 00:09:24) You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on G7: ====== ID#AAABnjuPPFw Vertex42 (2025-07-22 00:09:24) Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on H7: ====== ID#AAABnjuPPFk Vertex42 (2025-07-22 00:09:24) Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: ====== ID#AAABnjuPPFs End Date (2025-07-22 00:09:24) The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on J7: ====== ID#AAABnjuPPFg Vertex42 (2025-07-22 00:09:24) Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).